## Sheet1
week
39-40 | Create a trace from both up/downlink. | DONE
| Extract relevant data from the trace with Logtool or script. | TODO
| Rearrange the data in such a way that Matlab can read. | DONE
| Start analyzing the trace data. | STARTED
| Come up with requirements that the analyzer program will do. | STARTED
| Interview Jonas (an LTE expert) about what he wants us to accomplish and criteria he think we should fulfill in our analysis of the trace data. | TODO
| Select a suitable tool to build the analyzer in. | TODO
| Writing the end report. | STARTED
| Start building the analyzer. | TODO
41-42 | Extract relevant data from the trace with Logtool or script. | TODO
| Interview Jonas (an LTE expert) about what he wants us to accomplish and criteria he think we should fulfill in our analysis of the trace data. | TODO
| Select a suitable tool to build the analyzer in. | TODO
| Writing the end report. | STARTED
| Start building the analyzer. | TODO
| Evalutate if developing plugin to logTool is good | TODO
| Extract more relevant trace data from uplink and dowlink | TODO
| Try to get the script that either rickar or peter has done. | TODO