## Sheet1
week | Task | status | names | startdate | enddate | comments
38-39 | Create a trace from both up/downlink. | DONE | Paul & Razmus | 2014-09-19 | 2014-09-19
| Extract relevant data from the trace with Logtool or script. | TODO | Paul & Razmus
| Rearrange the data in such a way that Matlab can read. | DONE | Paul & Razmus | 2014-09-18 | 2014-09-18
| Start analyzing the trace data. | STARTED | Paul & Razmus | 2014-09-22
| Come up with requirements that the analyzer program will do. | STARTED | Paul & Razmus | 2014-09-22
| Interview Jonas (an LTE expert) about what he wants us to accomplish | TODO | Paul & Razmus
| Select a suitable tool to build the analyzer in. | TODO | Paul & Razmus
| Writing the end report. | STARTED | Paul & Razmus | 2014-09-20
| Start building the analyzer. | TODO | Paul & Razmus
40-41 | Extract basic data from the trace with Logtool or script. | DONE | Paul | 2014-10-01 | 2014-10-01
| Interview Jonas (an LTE expert) about what he wants us to accomplish | TODO | Paul & Razmus | 2014-10-17 |  | suggestion on start date on interview
| Writing the end report. | STARTED | Paul & Razmus | 2014-09-20
| build the analyzer-plugin to logtool in Java. | STARTED | Razmus | 2014-09-29
| Evalutate if developing plugin to logTool is good | STARTED | Paul & Razmus | 2014-09-26
| Get the script that either rickard or peter has done. | TODO/canceled | -
| research gui components in the plugin tool | STARTED | Razmus | 2014-10-02
| think of which trace data we want | DONE | Paul & Razmus
| Extract more trace data with relevant propsim settings | TODO | Paul & Razmus
| build basic analyzing script in Matlab | DONE | Paul & Razmus | 2014-10-01 | 2014-10-03
| build basic analyzing script in Java | (DONE) | Paul | 2014-10-08 | 2014-10-08
| Find more relevant articles about HARQ and LA | TODO | Paul & Razmus | 2014-10-09
| Plan interview | TODO | Paul & Razmus
42-43 | Interview Jonas (an LTE expert) about what he wants us to accomplish | TODO | Paul & Razmus
| Writing the end report. | STARTED | Paul & Razmus | 2014-09-20
| build the analyzer-plugin to logtool in Java. | STARTED | Razmus | 2014-09-29
| Evalutate if developing plugin to logTool is good | DONE | Paul & Razmus |  | 2014-10-10
| research gui components in the plugin tool | DONE | Razmus |  | 2014-10-06
| Extract more trace data with relevant propsim settings | DONE | Paul & Razmus |  | 2014-10-24
| Find more relevant articles about HARQ and LA | TODO | Paul & Razmus
| Plan interview | TODO | Paul & Razmus
44-45 | Interview Jonas (an LTE expert) about what he wants us to accomplish | DONE | Paul & Razmus
| Writing the end report. | STARTED | Paul & Razmus | 2014-09-20
| build the analyzer-plugin to logtool in Java. | STARTED | Razmus | 2014-09-29
| Find more relevant articles about HARQ and LA | STARTED | Paul & Razmus | 2014-10-27
| Plan interview | DONE | Paul & Razmus | 2014-10-27 | 2014-10-30
| plan analysation of Link Adaptation | STARTED | Paul & Razmus | 2014-11-03
| Plan analysation of HARQ | TODO? | Paul & Razmus
| Save graphs | DONE | Razmus |  | 2014-11-03
licensavtal för jfreechart, vad gäller. Höra med logtool
46-47 | create an realtime analyser in the plugin | TODO? | Razmus
| Writing the end report. | ONGOING | Paul & Razmus | 2014-09-20
| build the analyzer-plugin to logtool in Java. | ONGOING | Razmus | 2014-09-29
| Find more relevant articles about HARQ and LA | ONGOING | Paul & Razmus | 2014-10-27
| plan analysation of Link Adaptation (HARQ) | DONE | Paul | 2014-11-03
| fix the optional tab in the analyser | ONGOING | Razmus | 2014-11-10
| peter tries to install rickards automation script | STARTED | Peter |  | prel 20-nov
| try to fix system constant values | STARTED | Paul Raz & Peter
48-49 | create an realtime analyser in the plugin | TODO? | Razmus
| Writing the end report. | ONGOING | Paul & Razmus | 2014-09-20
| build the analyzer-plugin to logtool in Java. | ONGOING | Razmus | 2014-09-29
| Find more relevant articles about HARQ and LA | ONGOING | Paul & Razmus | 2014-10-27
| fix the optional tab in the analyser | ONGOING | Razmus | 2014-11-10
| peter tries to install rickards automation script | DONE | Peter/Paul | 2014-11-20 | 2014-11-27 | Paul instlled and fixed the script
| try to fix system constant values | DONE/CANCELED | Paul Raz & Peter | 2014-11-10 | 2014-11-27 | We have decided to skip the planned analysation on mcs and change it to just look att the bler target and througput correlation
| Demo for Ola and Johannes | TODO | Paul & Razmus | 2014-11-26 | prel 02-dec | Demo for Ola and Johannes at Ericsson the 2nd december
| plan the new analysation BLER target | TODO | Paul and Razmus | 2014-11-27
| Formulate the question (frågeställning) about the tool in report | TODO | Razmus | 2014-11-27 | prel 02-dec
| find a scientific base (articles) that the new analysation can be based on | TODO | Paul | 2014-11-27
50-51 | write questions to planneringsrapport
draw traces for the analysis on BLER target
create opimization function in the tool
writing on the end report
| create an enkät for testers. |  |  |  |  | the testers answer the enkät on how well designed the tool is.
make testers test our tool